## Sheet1
DIGITAL TECHNOLOGIES TASK 3 - PROGRAMMING
4 WEEK PLAN
| TOM T | ETHAN VB | BOTH
WEEK 1 | Artwork | More in-depth plan | Planning
| - 16x16 images for everything | - What exactly happens? | - What project are we doing?
WEEK 2 | HTML | JavaScript
| - Design a basic screen layout | - Give our game some basic functionality
WEEK 3 | CSS | JavaScript | GitHub
| - Div alignments, better monospace fonts, etc. | - Flesh out the basic prototype developed in wk2 into a full game | - Issues - Keeping up the commits
WEEK 4 |  |  | All code; marking key
- Bug fixes and finishing touches
- Make sure you have everything on the marking key